## Sheet1
Description	Date	Time	Notes
taking notes in class	04/07/14	1:20-2:35
setting up bitbucket, trello, time tracking, and work log		2:45-2:52, 4:10-5:20	Trying desparately to get started, but, honestly, panic attacks kept making focusing on getting anything done extremely difficult.
finishing setting up Trello		5:46-6:18
setting up Dropbox on Ubuntu.		06:24-6:40	For whatever reason, I was doing most of my previous documentation in Windows, so I'm trying to use Dropbox to move the files over.
set up bitbucket		6:40-7:40
Create work log and edit time tracking sheet to include date		7:40-7:48
development		7:49-8:21	Trying to figure out rvm, then creating the first branch to start development.
scrum meeting	04/08/14	1:05pm-1:20pm
orm diagram refresher		01:21-1:30
download ORM Designer		01:30-1:45?	ended up researching and installing wine as well. The install never ended up finishing. Guessing when I started on the next task.
creating .ruby-version and .ruby-gemset files		01:55-2:25	Working on this while waiting on ORM Designer install. Just realizing I don't HAVE to have a .ruby-version file. Blah.
Researching how to install MySql and use it via the terminal.		02:34-2:45	Was going to install MySQL, but Wine is still (trying) installing. So it's going to take a second before I can install sql through the terminal. Additionally, internet connection issues are making everything a ton slower.
Creating diagrams on paper		04:00-4:45	this includes taking the pictures
Installing and configuring MySQL		04:45-4:53
Researching and downloading MySQL Workbench		05:00-5:51	Dependency errors
Started creating database tables		05:51-5:04	Had to stop for dad's birthday dinner.
Getting back to db stuff		8:08-8:15
ingredient uml		08:15-8:28	realized I need another table for ingredients. Therefore, also need to figure out all food preferences now.
updated User uml 3hrs 45 min		08:28-8:36	this will include transfering ingredient uml and user uml to computer.
looking into if I should store arrays or collections in my db		09:10-9:13	answer=don't. Brainstorming time.
brainstorming db stuff		09:13-9:24	Multiple recipes have multiple ingredients, but ingredients can be put into multiple recipes. Hmmm.....many to many? Research time.
creating relation scheme diagram		9:25-9:39
Scrum meeting	04/09/14	1:00-1:13
more research on ORM		01:13-1:48	Yeah, decided I really need to learn more ORM stuff so that I can better map out my db before I even touch actually making it. This time includes working on understanding diagramming and going to talk to Jamie for ideas on how to do the many to many.
diagrams		01:57-2:14	needed to take a break
finally creating the db		02:14-2:54	Stopped to head home.
More of creating the db		04:47-4:52 8:45-9:30
double check that the database is correct on naming		9:45-10:10 10:20-11:00	Had to stop. Having database problems. It refuses to create my tables.
Scrum meeting	04/10/14	12:45-1:00
rebuilding db		01:06-2:10	db is finally done and fixed with a naming convention and all.
fixing rails versions		02:10-2:51 3:40-4:15	Was going to work on building the models, but many many errors have popped up. So I have to do this first.
starting making CRUD functions for recipes		04:15-4:50 5:05-5:30	Realized that I have to create the database through Ruby. But I still don't consider my time making a seperate db a waste because now I know exactly what I need to do
Scrum meeting	04/11/13	12:58-1:03
Understanding many to many relationships using ActiveRecord		01:12-1:50
research ActiveRecord validations and callbacks		01:50-2:34
making models		2:34-2:55 5:42-6:05	break because going home
creating model associations		06:05-7:11	ran into problems migrating models with ints and decimals
create model validations		08:30-10:15	still need to figure out how to do validation for ingredients in a recipe
Re-learning about branches and creating a new branch		10:40-10:50	forgot about branches till just now
reading the tutorial on git branches	04/12/14	03:20-3:54
update trello		03:54-4:03 4:39-4:45	had to take a break to meet with someone
create food controller and views		04:45-5:50
Continue working on food views	04/13/14	12:36-1:23	Found HUGE naming problems. Taking a break before tackling this.
Fixing naming		05:10-5:20
troubleshooting errors with create foods		05:20-6:05
food views		06:05-6:24
actually creating a foods list page		06:24-6:56
finishing up food views		06:56-7:02
creating partials		07:02-7:08
creating delete action		7:08-7:13
updating trello and making final changes on food		07:13-7:37 8:20-8:46	break for dinner. Also, trying to troubleshoot letting users know if they made changes
making all the stuff for recipes		8:46-9:26	stopping for the night because from here it'll be fun trying to get recipes and foods wired up
Scrum meeting	04/14/14	12:55-1:10
testing and fixing recipe CRUD stuff		01:10-1:20
weekly meeting		1:20-1:40	not exactly sure on times, but here's an educated guess
research user experience		08:21-8:27	quick brush up
creating list of people to ask and questions to ask		8:27-9:16	will do interviews over the next week
continuing fixing recipe CRUD things		09:16-10:16	doing this more to hammer out issues for later
fixing notifications	04/15/14	11:21-12:11	stuck. Will ask later.
Working on recipes CRUD		12:30-1:15	going to build the sample in order to better understand it. Also, might have found out how to fix notifications, so going to do that now
finish notifications		01:15-1:37
flailing around, trying to figure out how to do ingredients.		01:37-1:45
user crud stuff		01:45-2:55	taking a break to head home
more user crud stuff. And logins and whatnot		03:25-3:40	gotta go to work
Scrum meeting	04/16/14	1:05-1:25
user sign in and authentication		01:30-3:05	also set up question on stackoverflow to find out how to do ingredients in form
fixing b-crypt authentication		4:15-4:28
testing authentication		04:28-4:50	and trouble-shooting stupid mistakes
messing with trello and pushing current changes to bitbucket		4:50-4:53 PM
authorization	04/17/14	12:46-2:04	Wierd error is making it so edit and delete are visible, but only if I manually added the user id. Need to come back to this.
adding ingredients to recipes.		02:04-2:47	Note: need to redo validations and associations for users in a second. Also need to do validations for ingredients being entered.
trying to fix authorization bug		03:54-5:29	I give up on trying. I'll ask for help tomorrow.
sign up = auto log in		05:29-5:45
validations		5:45-5:55
UX interview – dad		5:55-6:17
UX interview – Vannah		6:50-6:53
UX interview – Vannah's sis		6:53-7:00
UX interview – mom		11:15-11:18
UX interview – Britt		11:34-11:43
Scrum meeting	04/18/14	1:10-1:25
Trying to fix authentication from scratch.		01:26-2:34
Changing my authentication to devise		02:34-2:55
UX interview – Haircutter		05:46-5:50
UX interview – Hillary		08:50-9:00
UX interview – Adrien		9:05-9:17
UX interview – Garret		11:15-11:17
UX interview – Brandon		11:17-11:23
UX interview – Melissa		11:25-11:29
trying to get ahold of people for UX interviews	04/19/14	12:55-1:03	Going to have to hold off on this until people can call me back.
Devise stuff		01:03-1:36	break for UX interview
UX interview – Doug		1:36-1:40
back to devise stuff		01:40-2:10	break for lunch
More Devise stuff		02:48-4:19	Aaaaaand, time to get ready for work
Fixing Devise errors		6:20-6:45	Want to make more progress before going to work
Devise.		10:51-11:20	…..can't solve this error for the life of me. Easier to completely uninstall devise and start over with it.
Starting over.		11:20-12:00	have to restart to see if the current error is due to a system issue...
Starting over cont.	04/20/14	12:00-2:00am
figuring out creating new branch w/o killing work done		2:00-2:05
UX interview – Cory		4:55-5:03
UX interview – Uncle Doug		5:05-5:09
UX Interview – Grandma		7:06-7:09
Devise		07:40-8:30
fix CRUD for recipes		08:30-9:00	still can't figure it out...
Tried looking briefly into CanCan and user permissions...		09:00-9:07
Scrum meeting	04/21/14	1:00-1:05
Talk with Aaron Reed		1:05-1:25
Meeting with Tim		1:25-1:40
Brainstorming		1:40-1:50
fixing worklog		01:50:1:56
Research recipe websites		01:56-3:06	allrecipes.com, foodnetwork.com, meals.com, postpunkkitcken.com, stumblupon, pinterest
brainstorming and research for ingredients		08:52-9:19	I'm going to let this simmer in my head for a little while...
fix CRUD for recipes		09:19-10:00	I'm not getting anything done...rawr.
Start implementing ingredients fix for CRUD	04/22/14	11:25-11:35 11:45-12:50	took a 10 minute break to talk with Scott because I never see him =(
fixing display of ingredients, editing only your own stuff, ect.		01:07-2:02
Users getting to eachother's profiles...		2:20-2:53	heading home
fix bugs		04:13-4:57	double update message, reset password, cleaner validation. Also making a gmail just as a temp for this project.
Working with CanCan		05:00-5:18	No, not all bugs are fixed. But I'm not making progress, so I'll come back to it...but got nothing done.
Cancan tutorial		08:45-9:15
implement admin boolean and make root admin		09:15-9:22
implement member boolean and set signed up users to member		09:22-9:33	didn't finish
closing shop		09:33-9:40	updating trello, work log, ect.
Scrum meeting	04/23/14	1:02-1:10
Working on CanCan		01:28-2:17	big blank area here was because helping Tj with his mockups. But break time.
More CanCan		02:31-2:50	need to finish CanCan for views and controllers...but have to go home now
And even more CanCan. Debugging.		04:29-5:16
destroy recipes from user when user destroys account		5:16-5:42	...no progress. Break time.
destroy recipes from user when user destroys account	04/24/14	01:00-1:53	FINALLY DONE!!!
Starting filtering		02:04-2:45	got basic filtering done for specific foods
closing shop		2:45-2:50	update trello, work log, bitbucket, ect
Scrum meeting	04/25/14	01:06-1:22
fix gitbucket branches		1:22-1:32
start vegan filtering/test		01:32-2:18 2:29-2:45	break time, and still have a lot to do
closing shop		2:45-2:50
working on fishing Vegan filtering	04/26/14	03:50-4:10	remembered that I have to make the users_preferences table
users_preferences table to make col when user sign up		4:10-4:55	no luck so far...
trying to find tutorial on nested resources		4:55-5:01	...break time.
working on users_preferences		05:42-6:31	...I need to clear my head.
Let's try this again. Users_preferences		7:12-8:00	Not getting anywhere. Moving on for now, ask questions later.
fill out preferences form		08:00-8:10
saving changes and checking status		8:10-8:14
work on preferences and try to fix it	04/27/14	05:08-5:45
recreating the usersPreferences table =(		5:45-5:59
follow tutorial for nested resources		05:59-6:39	also renaming to preferences for simplicity. But still stuck. Break time.
project log	04/28/14	12:45-1:00
Scrum meeting		1:00-1:08
updating git and trello		1:08-1:12
listening to Aaron		1:12-1:15
check in	04/29/14	1:00-1:30
research		1:30-2:00	might have found a solution, but sidestepping for a second
possible fix for password reset		02:00-2:30	no luck, sick of wasting time. Back to what I was doing.
more research Active Admin		02:30-2:37	...Active Admin might be useful later. But it doesn't really help with this problem.
research Will_Filter		02:37-2:45	time to go home...
more Will_Filter research		3:43-4:01
start implementing will_filter		04:01-4:20	break for dinner with relatives
will_filter		4:40-5:34	it appears will_filter is giving me routing errors. Time to look for a diff filter gem
look for filter gem		06:00-6:30	Filteriffic? Going to take a break to think about how I could use it.
looking into kaminari		7:10-7:38	well, it looks like the error was because of the will_filter gem...sad
looking into filter gems		07:38-7:54
Gonna try has_scope...please let this work		07:54-8:33	it's complicated to try to figure out how this where statement is going to work...
Trying to figure out where statement for filtering		08:54-9:05	starting to wonder if has_scope is really what I should be using....
quick css		09:05-9:59	commenting out work on filter, and just going to work on looks while brain processes. Taking break from this to pick up Britt.
Scrum meeting	04/30/14	1:05-1:15
fix ux mess		01:22-1:40
bootstrap		01:40-2:55
More bootstrap		03:55-4:40	Basic layout and resizing
Trying once again to figure out filtering		04:47-5:27	Still no luck, and just getting angry. Again.
trying to promote users to admins.		05:27-5:54	Okay. I'm getting absolutely nothing done. Break time.
let's see if I can even get filtering to work at all		06:27-7:00	so I can do filtering with a boolean. Lets try something more complicated.
trying to fix random errors because Kaminari and has_scope		07:00-7:21	pagination and filtering not playing nice with each other. Break time.
let's try to fix Kaminari and Has_Scope. Blah.		07:41-8:02	still not working.
emailing Tim for advice		08:02-8:06
Starting features list off of trello and UX interviews		10:10-10:25
remove duplicates and organize list		10:25-10:35
prioritize features list	05/01/14	01:05-1:13
apply features list to trello		1:13-1:22	note: not all features have been applied to trello yet, just the beginning (up to 6)
start working on getting preferences page to work		01:22-2:14	break time
back to work on Preferences		2:31-2:50	time to go home
and even more Preferences		4:12-4:35
fixing style on edit preference page		04:35-5:08
check preference page updating		05:08-5:27
clean up labels for preferences		05:27-5:54
check if validations are cleaner		05:54-6:00
random bugs		6:00-6:15
low low low fi mockups	05/02/14	11:30-11:45
Scrum meeting		1:10-1:20
filtering		1:20-2:50	time to go home and get ready for work
Filtering – adding isVegan and stuff		05:30-6:15	ended up running errands as well. Jeez, long break there
finish food preferences filter list	05/03/14	03:06-3:35
update trello		03:35-3:37
change foodsToFilter to blacklist		3:37-4:00
fix nested array problem		4:00-4:28
design		04:28-4:49	break time because frustration.
more design		5:41-6:03
switching over to breadcrumbs for a second		06:03-6:17
back to trying to get the background to change		06:17-6:42	now that I finally figured out why it wasn't changing, I'm going to move on.
styling site		6:42-7:09	feels like I'm wasting time. Moving on to something productive.
pictures for recipes		8:13-8:36	taking a break to go get a desk thingy for my laptop
continue Paperclip		10:17-10:28
notes on whitelist	05/04/14	04:05-4:08
Front-end		04:08-5:00
floating nav and fixing colors		05:17-5:41
fixing the suddenly missing pagination		05:41-5:45
back to fixing stylings for pages		05:45-5:56
more design and stuff		06:09-6:16	...I need my ankle wrap.
Fixing pagination for preferences for Root		6:20-6:28
checking all pages for style issues		06:28-6:36	people are showing up for family thingy...
Scrum meeting	05/05/14	1:12-1:20
weekly goals		1:20-1:30
fix pagination bug		1:30-1:40
completely redoing front-end		1:40-2:46	time to go home
add short descriptions var to recipes		03:43-4:26
add data to database		04:26-4:45	going to add more later when Britt is here because she has a lot more recipes.
Add a simple footer		04:45-4:50	lol break time
promote user to admin		05:22-5:52
have to take a break from admin and fix padding		05:52-5:56
fix breadcrumbs		05:56-6:20	yeah, not all of them are fixed
only admin access user index		6:20-6:31	I'm stuck.
fix admin access to user_profile		7:07-7:21
clean up code		07:21-7:45	doesn't look like it's going to happen. Sad.
breadcrumbs user profile		07:45-7:57
admin edit users		07:57-8:00
taking a break to merge and create new branch		08:00-8:13	strange errors with changing branches.
fixing more bitbucket problems. Arg.		8:13-8:33	Silly me, not realizing that I needed to push to master after changing branches. Wow.
admin edit users		09:00-9:30
fixing preferences		09:30-10:11	Aaaand, it's still broken. Great.
closing shop		10:11-10:15