## Sheet1
Description	Date	Time	Notes
taking notes in class	04/07/14	1:20-2:35
setting up bitbucket, trello, time tracking, and work log		2:45-2:52, 4:10-5:20	Trying desparately to get started, but, honestly, panic attacks kept making focusing on getting anything done extremely difficult.
finishing setting up Trello		5:46-6:18
setting up Dropbox on Ubuntu.		06:24-6:40	For whatever reason, I was doing most of my previous documentation in Windows, so I'm trying to use Dropbox to move the files over.
set up bitbucket		6:40-7:40
Create work log and edit time tracking sheet to include date		7:40-7:48
development		7:49-8:21	Trying to figure out rvm, then creating the first branch to start development.
scrum meeting	04/08/14	1:05pm-1:20pm
orm diagram refresher		01:21-1:30
download ORM Designer		01:30-1:45?	ended up researching and installing wine as well. The install never ended up finishing. Guessing when I started on the next task.
creating .ruby-version and .ruby-gemset files		01:55-2:25	Working on this while waiting on ORM Designer install. Just realizing I don't HAVE to have a .ruby-version file. Blah.
Researching how to install MySql and use it via the terminal.		02:34-2:45	Was going to install MySQL, but Wine is still (trying) installing. So it's going to take a second before I can install sql through the terminal. Additionally, internet connection issues are making everything a ton slower.
Creating diagrams on paper		04:00-4:45	this includes taking the pictures
Installing and configuring MySQL		04:45-4:53
Researching and downloading MySQL Workbench		05:00-5:51	Dependency errors
Started creating database tables		05:51-5:04	Had to stop for dad's birthday dinner.
Getting back to db stuff		8:08-8:15
ingredient uml		08:15-8:28	realized I need another table for ingredients. Therefore, also need to figure out all food preferences now.
updated User uml 3hrs 45 min		08:28-8:36	this will include transfering ingredient uml and user uml to computer.
looking into if I should store arrays or collections in my db		09:10-9:13	answer=don't. Brainstorming time.
brainstorming db stuff		09:13-9:24	Multiple recipes have multiple ingredients, but ingredients can be put into multiple recipes. Hmmm.....many to many? Research time.
creating relation scheme diagram		9:25-9:39
Scrum meeting	04/09/14	1:00-1:13
more research on ORM		01:13-1:48	Yeah, decided I really need to learn more ORM stuff so that I can better map out my db before I even touch actually making it. This time includes working on understanding diagramming and going to talk to Jamie for ideas on how to do the many to many.
diagrams		01:57-2:14	needed to take a break
finally creating the db		02:14-2:54	Stopped to head home.
More of creating the db		04:47-4:52 8:45-9:30
double check that the database is correct on naming		9:45-10:10 10:20-11:00	Had to stop. Having database problems. It refuses to create my tables.
Scrum meeting	04/10/14	12:45-1:00
rebuilding db		01:06-2:10	db is finally done and fixed with a naming convention and all.
fixing rails versions		02:10-2:51 3:40-4:15	Was going to work on building the models, but many many errors have popped up. So I have to do this first.
starting making CRUD functions for recipes		04:15-4:50 5:05-5:30	Realized that I have to create the database through Ruby. But I still don't consider my time making a seperate db a waste because now I know exactly what I need to do
Scrum meeting	04/11/13	12:58-1:03
Understanding many to many relationships using ActiveRecord		01:12-1:50
research ActiveRecord validations and callbacks		01:50-2:34
making models		2:34-2:55 5:42-6:05	break because going home
creating model associations		06:05-7:11	ran into problems migrating models with ints and decimals
create model validations		08:30-10:15	still need to figure out how to do validation for ingredients in a recipe
Re-learning about branches and creating a new branch		10:40-10:50	forgot about branches till just now
reading the tutorial on git branches	04/12/14	03:20-3:54
update trello		03:54-4:03 4:39-4:45	had to take a break to meet with someone
create food controller and views		04:45-5:50
Continue working on food views	04/13/14	12:36-1:23	Found HUGE naming problems. Taking a break before tackling this.
Fixing naming		05:10-5:20
troubleshooting errors with create foods		05:20-6:05
food views		06:05-6:24
actually creating a foods list page		06:24-6:56
finishing up food views		06:56-7:02
creating partials		07:02-7:08
creating delete action		7:08-7:13
updating trello and making final changes on food		07:13-7:37 8:20-8:46	break for dinner. Also, trying to troubleshoot letting users know if they made changes
making all the stuff for recipes		8:46-9:26	stopping for the night because from here it'll be fun trying to get recipes and foods wired up
Scrum meeting	04/14/14	12:55-1:10
testing and fixing recipe CRUD stuff		01:10-1:20
weekly meeting		1:20-1:40	not exactly sure on times, but here's an educated guess
research user experience		08:21-8:27	quick brush up
creating list of people to ask and questions to ask		8:27-9:16	will do interviews over the next week
continuing fixing recipe CRUD things		09:16-10:16	doing this more to hammer out issues for later
fixing notifications	04/15/14	11:21-12:11	stuck. Will ask later.
Working on recipes CRUD		12:30-1:15	going to build the sample in order to better understand it. Also, might have found out how to fix notifications, so going to do that now
finish notifications		01:15-1:37
flailing around, trying to figure out how to do ingredients.		01:37-1:45
user crud stuff		01:45-2:55	taking a break to head home
more user crud stuff. And logins and whatnot		03:25-3:40	gotta go to work
Scrum meeting	04/16/14	1:05-1:25
user sign in and authentication		01:30-3:05	also set up question on stackoverflow to find out how to do ingredients in form
fixing b-crypt authentication		4:15-4:28
testing authentication		04:28-4:50	and trouble-shooting stupid mistakes
messing with trello and pushing current changes to bitbucket		4:50-4:53 PM
authorization	04/17/14	12:46-2:04	Wierd error is making it so edit and delete are visible, but only if I manually added the user id. Need to come back to this.
adding ingredients to recipes.		02:04-2:47	Note: need to redo validations and associations for users in a second. Also need to do validations for ingredients being entered.
trying to fix authorization bug		03:54-5:29	I give up on trying. I'll ask for help tomorrow.
sign up = auto log in		05:29-5:45
validations		5:45-5:55
UX interview – dad		5:55-6:17
UX interview – Vannah		6:50-6:53
UX interview – Vannah's sis		6:53-7:00
UX interview – mom		11:15-11:18
UX interview – Britt		11:34-11:43
Scrum meeting	04/18/14	1:10-1:25
Trying to fix authentication from scratch.		01:26-2:34
Changing my authentication to devise		02:34-2:55
UX interview – Haircutter		05:46-5:50
UX interview – Hillary		08:50-9:00
UX interview – Adrien		9:05-9:17
UX interview – Garret		11:15-11:17
UX interview – Brandon		11:17-11:23
UX interview – Melissa		11:25-11:29